Potential Resource Issue:

Protection of bald eagles and their habitat.

Project Nexus:

Project operation and maintenance activities and potential Project betterments could affect bald eagles or their habitat.

Potential License Condition:

Bald Eagle Management Plan

Study Objective:

Document wintering and nesting bald eagles in the vicinity of Project reservoirs and large bypass and peaking reaches.

Determine whether Project communication lines and powerlines are consistent with Avian Power Line Interaction Committee (APLIC) Guidelines.

Document wintering and nesting bald eagles at potential Project betterments.

Extent of Study Area:

The study area for bald eagle includes ½ mile around reservoirs and on either side of river reaches listed below:

French Meadows Reservoir;

Hell Hole Reservoir;

Middle Fork Interbay;

Ralston Afterbay;

Rubicon River from Hell Hole Reservoir to MFAR confluence;

MFAR and from French Meadows Reservoir to the confluence with North Fork American River (NFAR), and;

NFAR confluence to the Ordinary High Water Mark (OHWM) of Folsom Reservoir.

Study Approach:

Identify and map known occurrences of bald eagles, roosts, and nests within the study area, based on agency consultation and a review of existing information.  Preliminary information is presented in the Middle Fork American River Project (FERC No. 2079) Draft Existing Resource Information Report, First Series (PCWA 2006).

Map the location of Project communication lines and powerlines and determine if they are consistent with APLIC Guidelines (see TERR 4 – Special-Status Wildlife Technical Study Plan (TSP)).

Conduct protocol-level bald eagle wintering and nesting surveys according to the Protocol for Evaluating Bald Eagle Habitat and Populations in California (Jackman and Jenkins 2004).  A summary of the survey requirements is provided below.

Bald Eagle Wintering Surveys

Wintering surveys will consist of two types of surveys—wintering bird surveys and winter roost surveys.

  - Wintering Bird Surveys

Single-day surveys will be conducted monthly from December through February (three surveys, at least two weeks apart).  Unless weather prohibits safe surveys, the January survey will be conducted during the USFWS two-week nationwide bald eagle winter survey to allow comparisons with statewide population trends.  Surveys will be completed from a helicopter or boat, depending on weather conditions and accessibility.  Data will be recorded on data sheets developed by Zack et al., 1997, as modified by Jackman, et al., 2001.

  - Winter Night Roost Surveys

Winter night roost surveys will be conducted once a month (December through February) in areas where wintering eagles are observed.  To find potential night roost areas, bald eagles will be visually observed as they move from foraging habitat to potential night roosts in the late afternoon.  The number of eagles entering the probable night roost will be recorded.

Probable night roost areas will be revisited the following morning for at least two hours beginning one-half hour before sunrise.  Eagles observed returning to foraging habitat will be counted.  Once a forest stand is identified as a probable night roost, a daytime survey will be conducted to look for evidence of use by bald eagles (feathers, castings) and to GPS or pinpoint the location used for roosting.

Bald Eagle Nesting Surveys

The objective of bald eagle nesting surveys is to monitor the breeding status of existing nests and to locate any new nests.  The result of each survey will be reported on the CDFG Bald Eagle Nesting Territory Survey Form.

  - Determine New Nests and Occupancy of Existing Nests

Conduct a survey in late February through March (as early in the season as possible, but contingent upon weather conditions) to determine whether the survey area (suitable breeding habitat) is occupied by bald eagles and if so, to determine their breeding status.  The survey shall include observations of any old nests, as well as identification of any new nests in the area.  Presence or apparent absence of adult bald eagles, courtship behavior, and nest construction will be recorded.

  - Determine Presence of Eggs/Nestlings

Conduct a survey during the mid-nesting season, late April through May, to determine the presence of eggs/nestlings in known nests.  All nesting sites documented in the initial survey will be evaluated to determine the presence of adults and number of eggs and/or nestlings.

  - Determine Nest Success

Conduct a survey during the late nesting season, early June through early July, to determine nest success.

Develop a GIS map of bald eagle wintering and nesting sites.

Overlay GIS information on Project facilities and features, recreation facilities, other dispersed concentrated use areas, bypass and peaking reaches, and potential Project betterments (see Tables TERR 1-1, TERR 1-2, TERR 1-3, and TERR 1-4).

Prepare and submit California Native Species Field Survey Forms for all bald eagles recorded to California Natural Diversity Data Base.

Prepare draft and final technical reports describing study objectives, methodologies, and results.

Schedule:

| Date | Activity |
| --- | --- |
| December 2007 through February 2008 | Conduct winter and winter roost field surveys |
| Late February through early July 2008 | Conduct nesting surveys |
| August through October 2008 | Analyze data and prepare draft report |
| October 2008 | Distribute draft report to the Terrestrial TWG |
| November 2008 through January 2009 | Terrestrial TWG review and provide comments on draft report |
| February and March 2009 | Resolve comments and prepare final report |
| March 2009 | Distribute final report to the Terrestrial TWG and Plenary |

References:

Jackman, R.E., and J.M. Jenkins.  2004.  Protocol for Evaluating Bald Eagle Habitat and Populations in California.

Placer County Water Agency (PCWA).  2006.  Middle Fork American River Project (FERC No. 2079) Draft Existing Resource Information Report, First Series.  June 2006.