Potential Resource Issue:

Visual quality.

# Project Nexus:

The presence of Project facilities, features, and operations could affect visual quality.

# Potential License Condition:

Visual Resources Plan

# Study Objectives:

Identify, map, and describe United States Department of Agricultural - Forest Service (USDA-FS) inventories associated with existing Project facilities features, and potential Project betterments.

Document the existing visual condition (EVC) of all Project facilities and features from associated viewsheds.

# Extent of Study Area:

The study area will include the Project facilities and features identified in Table REC 5-1 and their associated viewsheds.  The viewsheds include travel routes, recreation areas, and water bodies from which the existing Project facilities and features are visible to the public.

The study area will also include potential Project betterments, including new facilities, roads and trails, staging and construction work sites, as identified in Table REC 5-2, and new inundation area associated with the Hell Hole Reservoir Seasonal Storage increase.  .  The Hell Hole Reservoir Seasonal Storage Increase would raise the maximum operating WSE at Hell Hole Reservoir by 10 feet.

# Study Approach:

USDA-FS currently uses the Visual Management System (VMS) to address aesthetic resources.  However, the USDA-FS is moving towards a new system, the Scenery Management System (SMS).  The SMS will be incorporated into the Tahoe National Forest (TNF) Land and Resource Management Plan (LRMP), which is scheduled to be updated in 2008 or 2009.

The USDA-FS met internally to discuss whether PCWA should utilize the VMS or the SMS.  During the November 13, 2006 Recreation Technical Working Group (TWG) meeting, the USDA-FS recommended that PCWA use the VMS based on direction provided by the Regional Landscape Architect.  Therefore, this Technical Study Plan is based on the VMS.

USDA-FS VMS Inventories

In coordination with the USDA-FS, identify and map all sensitivity level 1 and 2 viewsheds in the study area, including those associated with existing Project facilities, features, and potential Project betterments.

Map and summarize the Eldorado National Forest (ENF) Land and Resource Management Plan (LRMP) and Tahoe National Forest (TNF) LRMP Visual Quality Objectives (VQOs) in the study area.

Identify and summarize the USDA-FS land management direction associated with the VMS inventories relative to the existing Project facilities, features, and potential Project betterments.

Map the location of existing Project facilities, features, and proposed Project betterments with respect to their associated viewsheds and VMS inventories including VQOs, variety classes, sensitivity levels, and distance zones.

Existing Visual Condition

Document the EVC of all existing Project facilities and features from associated viewsheds.

In consultation with the USDA-FS, identify key observation points (KOPs) and photograph the existing Project facilities and features using agreed upon photographic protocols.  Map and describe the locations of the KOPs.

At Project reservoirs that undergo seasonal water level fluctuations (i.e., French Meadows and Hell Hole reservoirs), photograph the reservoirs from KOPs at full pool and lowest expected pool.

Narratively describe water level fluctuations at Ralston Afterbay, including both daily and seasonal changes, and during maintenance outages.  In consultation with the stakeholders, determine whether it is necessary to photo-document water level changes at Ralston Afterbay.

Contingency Study – Photo-Document Water Level Changes at Ralston Afterbay

In consultation with the stakeholders, determine specific KOPs from which water levels at Ralston Afterbay should be photographed.

Photograph Ralston Afterbay at a range of water levels from specific KOPs.

# Schedule:

| Date | Activity |
| --- | --- |
| VMS Inventories and Existing Visual Conditions Assessment |
| October 2007 and July 2008 | Identify KOPs associated with French Meadows and Hell Hole reservoirs in coordination with USDA-FS. Photograph Hell Hole and French Meadows reservoirs at low and high water levels |
| November 2007 through July 2008 | Conduct VMS inventory in coordination with USDA-FS |
| July through September 2008 | Conduct field surveys documenting EVC of existing Project facilities. |
| October and November 2008 | Analyze data and prepare draft report |
| November 2008 | Distribute draft report to the Recreation TWG |
| December 2008 through February 2009 | Recreation TWG 90-day review and comment period |
| February and March 2009 | Resolve comments and prepare final report |
| April 2009 | Distribute final report to the Recreation TWG and Plenary |
| Contingency Study - Water Level Changes at Ralston Afterbay |
| February and March 2008 | Consult with the resource agencies to determine need to photo-document water level changes at Ralston Afterbay |
| March 2008 through April 2009 | Conduct field surveys, analyze data, prepare and distribute draft and final reports |

Level of Effort and Cost:

To be determined.

References:

Placer County Water Agency (PCWA).  2006.  Middle Fork American River Hydroelectric Project (FERC No. 2079) Draft Existing Resource Information Reports, Second Series.

United States Department of Agriculture Forest Service (USDA-FS).  1973.  National Forest Landscape Management (Volume 1).

USDA-FS.  1974.  National Forest Landscape Management (Volume 2, Chapter 1): The Visual Management System (Agricultural Handbook 462).

USDA-FS.  1995.  Landscape Aesthetics.  A Handbook for Scenery Management.  (Agricultural Handbook 701).