Potential Resource Issue:

Recreation opportunities.

Project Nexus:

The licensee has the responsibility to provide recreation opportunities.

Potential License Condition:

Recreation Plan

  - Recreation instream flows

  - Reservoir water surface elevations

  - Flow information dissemination

  - Interpretive materials and measures

  - Access improvements

  - Fish stocking

Study Objectives:

Conduct a General Visitor Survey.

  - Collect recreation visitor survey data to describe current recreation activities and characteristics of users at developed Project recreation facilities, at specific dispersed concentration use areas and at five locations within the Auburn State Recreation Area (ASRA).

  - Collect recreation user survey data to evaluate use patterns, visitor preferences and demand for opportunities, and new or improved developed recreation facilities.

Conduct an angler survey at French Meadows and Hell Hole reservoirs.

Extent of Study Area:

Recreation visitor surveys will be conducted at the existing developed Project recreation facilities and at select dispersed concentrated use areas identified in Table REC 2-1. In addition, recreation visitor surveys will be conducted at five specific sites located within the boundaries of the ASRA, as shown on Table REC 2-1.  The selection of dispersed concentrated use areas to be surveyed will be completed in consultation with the Recreation TWG participants after reviewing the results of vehicle counts and other information collected as part of the REC 1 – Recreation Use and Facilities Technical Study Plan (TSP).

Study Approach:

General Visitor Survey

Recreation visitor surveys will be conducted at developed Project recreation facilities and at five sites located within the ASRA, as identified in Table REC 2-1.  In addition, surveys will also be conducted at select dispersed concentrated use areas to be identified in consultation with the resource agencies pending the results of the vehicle counts to be conducted as part of the REC 1 – Recreation Use and Facilities Assessment TSP.  The design for implementing the visitor surveys will be developed after recreation use data have been collected as part of the REC 1 – Recreation Use and Facilities Assessment Technical Study so that the use data can be used to help determine the number of surveys to be completed at specific locations throughout the study area.

A preliminary list of information to be collected and potential issues to be addressed through visitor surveys is shown in Table REC 2-2.  This list was developed by PCWA in consultation with the stakeholders and will be used to develop the survey instrument(s) (questionnaires).  The survey instrument(s) will be developed and refined in consultation with the resource agency recreation specialists and other stakeholders prior to initiating the visitor surveys in 2008.

The survey instrument(s) will be developed in three steps, as follows:

Develop a draft General Visitor Survey instrument and survey implementation protocols (e.g. sampling frequency, sampling locations, type of survey) in coordination with a subgroup consisting of resource agency recreation specialists and other interested stakeholders.

Pretest the draft General Visitor Survey instrument to ensure that question wording is clear and unambiguous and that the survey completion time is reasonable (e.g., does not exceed 10 minutes).  The pretest would be completed at select locations in the study area in February or March of 2008, after the survey instrument is developed, and before implementing the General Visitor Survey.

Discuss the pretest results and finalize the General Visitor Survey instrument and survey implementation protocols in consultation with the Recreation TWG, including resource agencies.

PCWA expects to develop a draft General Visitor Survey instrument by November 2007.  Upon completion, the draft survey instrument will be incorporated into this TSP and the language of this TSP will be revised accordingly.   The revised TSP and draft General Visitor Survey instrument will be included the Pre-Application Document (PAD), which is due to be submitted to the FERC in December 2007.

The General Visitor Survey will be conducted at the developed Project recreation facilities, select dispersed concentrated use areas and five sites in ASRA using a stratified random sampling approach.  This survey would focus on collecting information identified in Table REC 2-2.  Specific data to be collected through surveys will be further refined in coordination with the Recreation TWG and subgroup as the survey issues are defined and the survey instrument is developed.

The General Visitor Survey would be conducted during the peak recreation season from Memorial Day through Labor Day.  Note that the Oregon Bar access site in ASRA is not due to be completed until some time in 2008.  Surveys at this location will begin after the site is completed and operational, which may be after Memorial Day.   The survey duration may be extended if specific informational needs for the shoulder seasons warrant.  The decision to extend the survey period will be made in consultation with the Recreation TWG.

As noted in Table REC 2-2, the General Visitor Survey will collect data to address issues involving specific user groups or activities, including angling, hunting, swimming, wading, hiking, horseback riding, mining, boating, and stream side activities such as picnicking.  The Visitor Survey outlined in this TSP focuses on collecting information by intercepting recreation visitors participating in a variety of activities at specific locations identified in Table REC 2-1.  Additional information specific to different user groups, such as whitewater boaters, stream anglers, and equestrians will be developed by conducting structured focused group sessions with representatives of these user groups, as part of the REC 4 – Stream Flow and Opportunities TSP.

Reservoir Angler Survey

A separate angler survey will be conducted at French Meadows and Hell Hole reservoirs.  The angler survey instrument will be developed in consultation with the California Department of Fish and Game (CDFG), the USDA-FS, and interested recreation TWG participants, and will focus on documenting angler effort, success, preferences, and satisfaction.  As with the General Visitor Survey, this survey would be conducted between Memorial Day and Labor Day.  The number of surveys to be completed, and the survey frequency, will be determined based on the results of the use data collected as part of the REC 1 – Recreation Use and Facilities Assessment TSP.

Schedule:

| Date | Activity |
| --- | --- |
| September 2007 through November 2007 | Develop/refine draft survey instrument and survey implementation protocols |
| February or March, 2008 | Pre-test survey instrument |
| May (Memorial Day) through September (Labor Day) 2008 | Conduct recreation visitor surveys and angler surveys |
| October 2008 through February 2009 | Analyze data and prepare draft report |
| March 2009 | Distribute draft report to the Recreation TWG |
| March and April 2009 | Recreation TWG review and provide comments on draft report |
| May and June 2009 | Resolve comments and prepare final report |
| July 2009 | Distribute final report to the Recreation TWG and Plenary |

Level of Effort and Cost:

To be determined.

References:

None.