Bypass Reach Whitewater Boating Flow Studies

Proposed Implementation Process

Rubicon River – Ellicott Bridge to Ralston Afterbay**

| Task | Timing | Responsible Party |
| --- | --- | --- |
|  |  | PCWA | Boating Study Team |
| Development of Study Forms and Identification of Study Team |
| Develop Draft Boater Profile and Flow Study Evaluation Forms | November 2009 | X |  |
| Identify potential boating study team participants |  |  | X |
| Finalize Boater Profile and Flow Study Evaluation Forms | December 2009 | X |  |
| Develop notification procedures |  | X |  |
| Identify transportation options |  | X | X |
| Confirm boating study team members |  |  | X |
| Distribute Boater Profile Forms, liability waivers, notification process, and study itinerary to confirmed boating study team members | January 2010 | X |  |
| Condition Monitoring |
| Monitor snowpack, weather conditions, flows, and reservoir levels to assess runoff conditions and/or potential for spill event. | Weekly beginning in January, increasing frequency as conditions change. | X |  |
| Provide updates to boating team members about runoff conditions and probability and timing of spill event. |  | X |  |
| Confirm target date(s) for flow study based on expectations regarding runoff conditions or spill event. | Condition dependent | X |  |
| Study Mobilization |
| Confirm and schedule transportation | As soon as target study date is identified. | X | X |
| Distribute final flow study itinerary to confirmed boating team members. |  | X |  |
| Meet boating team at pick-up point, shuttle to put-in, conduct pre-study briefing, and implement flow study. | Study date | X | X |
| Meet boating team at take-out, complete flow study evaluation forms, conduct post-run discussion, shuttle boating team to pick-up point. |  | X | X |
| Reporting |
| Prepare and distribute Draft report documenting study methods and results. | Within 6 weeks of study date. | X |  |

** 	A similar implementation process and schedule will be developed for the Middle Fork American River whitewater boating flow studies in early 2010.

# Text boxes

HANDOUT #2