Action Items

| TSP | Study Element | Action Item | Meeting Date during which Action was Discussed | Status | Notes |
| --- | --- | --- | --- | --- | --- |
| REC 4 | Flow Studies | Revise Draft Flow Study Forms as follows: More space to write regarding portages Estimate flow at put-in, take-out, mid-point | 11/17/09 | Complete | Revised forms posted to web site on December 16, 2009. |
| REC 4 | Flow Studies | Study Implementation Use laminated maps and orthophotos to identify portages and major rapids. Encourage boaters to carry/use GPS Try to get consensus from boaters on flow range during post run discussion. | 11/17/09 | Ongoing | To be completed during study. |
| REC 4 | Flow Studies | Study Logistics Andy/Nate coordinate regarding transportation options/logistics | 11/17/09 | Complete | Coordination in progress. Final logistics dependent upon timing of study and size of study team. |
| REC 3 | TSR | Revise report as follows: Add note to reservoir tables stating that minimum operating WSE has never been reached. Correct y scale on Box & Whisker plots Add min and max WSEs to hydrographs Add elevations that correspond to storage on WSE requirements tables. | 11/17/09 | Complete | Draft TSR distributed on December 22, 2009. |

| TSP | Study Element | Action Item | Meeting Date during which Action was Discussed | Status | Notes |
| --- | --- | --- | --- | --- | --- |
| REC 2 | Visitor Surveys | Conduct simple analysis to identify whether individual or group responses bias survey results. L. Lubetkin to contact SW research center regarding specific questions that could be tested. | 10/5/09 | Ongoing | Response to comments in progress. |
| REC 4 | Flow Studies | Document the range of solutions necessary to modify lower outlet infrastructure at Hell Hole Dam to allow for increased flow releases. | 5/29/08 | Ongoing |  |