Potential Resource Issue:

Protection of special-status bat roosts.

Project Nexus:

Project operations and maintenance activities and potential Project betterments could result in disturbance or removal of special-status bat roosts.

Potential License Condition:

Special-status bat protection measures

Study Objective:

Document of special-status bat roosts at existing Project facilities, features, and recreation facilities.

Document special-status bat roosts at potential Project betterments.

Extent of Study Area:

The study area includes Project facilities and features, and recreation facilities (see Existing Project Description Table 5-1 and Table 5-2).  If additional Project facilities, features, and recreation facilities are identified following submittal of the Pre-Application Document (PAD) to FERC, these areas will be surveyed consistent with this technical study plan.

The study area also includes buffer areas (100 feet) around potential Project betterments, including new facilities, roads, and trails; staging and disposal sites; as well as new inundation areas (see Existing Project Description, Proposed Project Betterments Table 6-1).

Study Approach:

Identify and map known occurrences of special-status bat populations based on agency consultation and a review of existing information.  This information is presented in the Middle Fork American River Hydroelectric Project (FERC No. 2079) Draft Existing Resource Information Report, First Series (PCWA 2006).

Conduct an evaluation of Project facilities and features, recreation facilities, and potential Project betterments, in consultation with the Terrestrial Working Group (TWG), to identify locations potentially supporting special-status bat roosts (i.e., areas for focused surveys).

Use multiple survey techniques to determine the presence/absence of special-status bat species, as well as general assemblage of bats.  Two types of surveys will be completed: reproductive surveys and seasonal patterns of use surveys.  Sampling methods will include acoustic sampling and mist netting. Each of these is described below.

Prepare draft and final technical reports describing study objectives, methodologies, and results.

Reproductive Surveys

Conduct roost surveys at locations identified by a qualified bat expert as potentially supporting special-status bats during the summer reproductive season (August through September) when maternal colonies may be present.  Each location will be searched for bats or bat signs (i.e., guano, characteristic staining, and culled insect parts).  Any location where bat species cannot be determined from a visual evaluations will be monitored at emergence time using mist netting and acoustic equipment.

Acoustic Sampling

Conduct acoustic sampling (i.e., sampling of echolocation calls) during the summer reproductive season at Project facilities, features, recreation facilities, and potential Project betterments identified as potentially supporting special-status bat species.

  - Acoustic sampling will be conducted using an Anabat II bat detector system (Titley Electronics) to identify bat species.  The Anabat system detects bat ultrasonic echolocation calls in the field and uses a z-caim unit to convert the detected signals into time/frequency (kilohertz (kHz)) graphs on a laptop computer.  Acoustic units (Anabat bat detector, z-caim, and laptop) will be placed in appropriate settings to collect bat calls.

  - Acoustic units will be operated for five nights per location from sunset until sunrise.

Mist Net Sampling

Conduct nighttime mist net sampling at Project facilities and features, recreation facilities and potential Project betterments identified as potentially supporting special-status bat species to determine species assemblage during the reproductive season.

  - Mist nets will be set up for one night, from sunset to 1 AM, in locations where active roosts are identified.

  - Captured bats will be identified to species.  Other information collected will include sex, age (juvenile or adult), reproductive status, and forearm measurements.

  - Captured bats will be released on-site and echolocation calls recorded at the time of release.

Seasonal Use Surveys

Conduct an additional survey in October at those locations where active roosts are identified during roost surveys to determine seasonal patterns of use.  This survey will include using mist nets and acoustic equipment as described above.

Develop a Geographic Information System (GIS) map of special-status bat roosts and overlay information on Project facilities and features, and recreation facilities, and potential Project betterments.

Prepare and submit California Native Species Field Survey Forms for all special-status bats recorded to California Natural Diversity Data Base.

Schedule:

| Date | Activity |
| --- | --- |
| June and July 2007 | Conduct facility, feature, and betterment survey |
| August and September 2007 | Conduct reproductive surveys |
| October 2007 | Conduct seasonal patterns of use surveys |
| November 2007 through February 2008 | Analyze data and prepare draft report |
| February 2008 | Distribute draft report to the Terrestrial TWG |
| March through April 2008 | Terrestrial TWG review and provide comments on draft report |
| May through June 2008 | Resolve comments and prepare final report |
| June 2008 | Distribute final report to the Terrestrial TWG and Plenary |

Level of Effort and Cost:

To be determined.

References:

Placer County Water Agency (PCWA).  2006.  Middle Fork American River Hydroelectric Project (FERC No. 2079) Draft Existing Resource Information Report, First Series.  June 2006.